## Slide 1: Module 4 - Managing Agile Digital Service Contracts: Oversight, Performance, and Delivery
Presented by: [Facilitator Name]
Date: [Session Date]

## Slide 2: Module 4 Performance Outcome
Manage vendor partnerships and support delivery through contract administration practices grounded in Agile and lean methodologies. Track project health using real-time, objective indicators, support continuous delivery, and adapt to change while ensuring alignment with mission goals. Focus on transparency, collaboration, and outcomes throughout the contract lifecycle.

## Slide 3: At the conclusion of this module, you will be able to
Explain the role of product ownership in Agile delivery and how it supports post-award success
Describe how product owners, CORs, and vendors collaborate using Agile tools and team rituals
Identify Agile performance metrics that go beyond compliance to measure true delivery value
Compare traditional and Agile performance measurement methods, including QASP alternatives and real-time metrics
Outline strategies to launch a new digital services contract with the right people, tools, and processes in place
Recognize early signs of delivery issues and explain approaches to address performance concerns in Agile environments

## Slide 4: Management of Digital Service Delivery Sprint 1

## Slide 5: Agile Rituals and Procurement Alignment
Presented by: [Facilitator Name]
Date: [Session Date]

## Slide 6: Agenda
Define the role of product ownership in federal digital service delivery.
Explain how Contracting Officer’s Representatives (CORs) and Product Owners (POs) collaborate to support Agile delivery.
Describe the importance of communication, shared understanding, and Agile rituals in cross-functional teams.
Identify ways to help teams celebrate progress and recognize success in Agile environments.

## Slide 7: The CO’s Role in Agile Doesn’t End at Award
Agile delivery requires ongoing involvement, not a handoff.
COs support alignment, risk management, and team coordination.
Success depends on shared visibility and adaptive decision-making.
Notes: Speaker Notes:
In traditional acquisitions, we often think of contract award as the finish line for the CO. But in Agile digital service delivery, it’s just the starting point.
As the Contracting Officer, your role evolves—you’re no longer just enforcing terms. You’re helping ensure the contract structure supports iterative delivery, evolving requirements, and product success.
That means being actively involved in key touchpoints: sprint reviews, demos, retrospectives—not just to observe, but to stay aware of risks, blockers, or scope shifts that may require contractual action.
You’ll work closely with the COR and PO. The COR will track performance data and team health; the PO will steer the backlog and user priorities; and you’ll ensure all of that remains anchored in the contract.
Agile delivery is adaptive by nature. You’re not managing a list of fixed outputs—you’re supporting a living product that evolves based on user feedback and technical feasibility. Your presence keeps that process grounded in acquisition integrity and mission outcomes.
That’s why post-award engagement isn’t optional—it’s a strategic lever.

## Slide 8: Activity: Who Does What? Agile Role Round Robin
Instructions
Participants are divided into breakout groups.
Each group receives 2–3 realistic Agile delivery prompts.
Roles are rotated for each scenario: PO, COR, CO, and Vendor.
Each person answers: "What should this role do in this situation?"
Quickly discuss the answers to identify and correct any unclear answers.
Notes: Speaker Notes: **This can be done virtually or in-person. This activity is accompanied by a participant worksheet.
Next up, we’re going to dive into an activity called ‘Who Does What? Agile Role Round Robin.’ This is a chance to explore the real-world decision-making that happens across Agile roles during delivery—especially between federal and vendor team members.
You’ll rotate through several scenarios in small groups, taking turns playing key roles like Product Owner, COR, Contracting Officer, and Vendor.
The goal isn’t to ‘get the answer right’—it’s to think critically about who owns what in Agile delivery and where role boundaries blur.
Expect to surface some tensions or overlaps. That’s normal—and valuable. We’ll unpack what those moments mean in the debrief.
Ready? Let’s get started!

## Slide 9: Let’s Debrief
Share one scenario your group explored.
What insight or surprise emerged about role clarity?
What tools, agreements, or structures could reduce future confusion?
Notes: Speaker Notes: Let’s come back together and debrief a bit.
I’d love for each group to share one scenario you explored and a key insight that came out of the conversation. Maybe it was a moment where roles weren’t clear… or maybe someone in the group brought a new perspective that shifted how you thought about accountability.
After that, we’ll reflect together on what we noticed across the board.
Some questions to think about: – Where did responsibilities overlap? – What helped you figure out who should take action? – And what kinds of tools or team agreements could make this clearer in your agency or with your vendors?
The big takeaway here is that shared understanding—early on—prevents slowdowns later. Having clarity doesn’t mean eliminating every gray area, but it does mean deciding how you’ll navigate those areas as a team.

## Slide 10: Activity: Build Your Charter Together
Instructions
Form small groups of 3–4 and take on the roles of CO, COR, and PO.
Use the provided scenario and charter template to complete four sections:
  Define the mission and project success.
  Clarify roles and shared responsibilities.
  Build a communication rhythm.
  Set escalation and celebration plans.
Use your real-life experience to shape how you collaborate.
Be ready to share a key takeaway or insight from your group.
Notes: Speaker Notes: **This can be done virtually or in-person. This activity is accompanied by a participant worksheet.
Now we’re going to simulate something that rarely happens but should—building a shared charter at the start of a project.
In small groups, you’ll take on the roles of the Product Owner, Contracting Officer’s Representative, and Contracting Officer, and work together to fill out a simple charter.
This is your chance to align on what success looks like, who owns what, and how you’ll work together throughout delivery.
Just like in real life, you might not agree on everything at first—that’s part of the learning. The conversations you have will be just as valuable as what you write down.
We’ll give you a short project scenario and a charter template to work from. Let’s get into groups and start building!

## Slide 11: Let’s Debrief
What felt easiest to align on? What took negotiation?
How did your team handle areas of overlap or uncertainty?
What elements of this charter could improve your next project kickoff?
Notes: Speaker Notes: Invite 1–2 groups to share highlights before opening to general discussion.

## Slide 12: Performance Measurement under Agile Delivery Contracts Sprint 2

## Slide 13: Using Methods and Metrics to Measure Performance in Agile Delivery
Presented by: [Facilitator Name]
Date: [Session Date]

## Slide 14: Agenda
Identify metrics creation and utilization to help identify when failure actually occurs.

## Slide 15: Why Agile Metrics Matter
Traditional compliance metrics is not the same as Agile performance.
Agile metrics validate value delivered, not just activity completed.
Effective metrics help:
  Support contract decisions
  Monitor delivery health in real time
  Align contractor performance with mission goals
Notes: Speaker Notes: Let’s kick things off with why we’re even talking about metrics in Agile procurement. Traditional contracting often focuses on whether a task was done ‘on time’ or ‘on budget.’ Agile asks a deeper question: Did this deliver real value to users and mission? That’s what our metrics need to measure—value, flow, and outcomes.

## Slide 16: Modern Metrics at a Glance

## Slide 17: Agile Metrics Toolbox
Value Stream & DevOps Metrics
Deployment Frequency
Lead Time for Changes
Flow Time & Flow Efficiency
Product Value Metrics
User Adoption
User Satisfaction
Business Value Delivered
Team Health Metrics
Sprint Completion Rate
Team Velocity Consistency
Issue Resolution Time
Notes: Speaker Notes: Here’s a high-level view of modern metrics categories. You don’t need to track everything—just focus on a few high-impact ones. These help tell the story of how fast value is flowing, whether users are benefiting, and how well the team is working together. Which of these stand out to you as useful for a contract you're currently managing?

## Slide 18: Incentivizing What Matters
Monetary Incentives:
Award fees tied to DORA or adoption metrics
Sprint-based performance rewards
Bonuses for team stability
Non-Monetary Incentives:
Greater autonomy and reduced oversight
Public recognition or future opportunities
Access to agency resources or innovation initiatives
Notes: Speaker Notes: Incentives should reinforce good behavior—not just reward outputs. The best contracts create a structure that motivates teams to continuously deliver value. Think about what success really looks like in your environment—and how to incentivize that, not just compliance.

## Slide 19: Let’s Discuss
What behavior are you trying to incentivize—and does your current contract structure support it?
Notes: Speaker Notes: whole group discussion - 15 minutes What we reward is often what we get. If we design a contract structure that rewards speed above all else, we might get fast delivery but not necessarily quality or usability. If we reward perfect documentation, we might get thorough paperwork but maybe less responsiveness to user needs.
The question we’re exploring today is: What behavior do you actually want from your vendors and partners—and does your contract make that behavior likely, or does it unintentionally discourage it?
Examples
“If you want continuous improvement, do your payment milestones or evaluation metrics allow vendors to adapt over time—or do they lock them into a rigid upfront plan?”
“If you want collaboration with your in-house team, does the contract allow time and budget for that, or does it only reward hitting delivery dates?”
“If you want user-centered design, are there incentives for testing with real users, or is it all about passing internal reviews?”
Prompt participants:
“What’s an example from your own work where the incentives matched the desired behavior well?”
“What’s an example where the incentives worked against the intended behavior?”
“If you could redesign your current contract, what’s one small change that would better align it with your goals?”
Encourage participants to consider both vendor behavior and government team behavior.
Takeaways
“The big idea here is that incentive structures aren’t neutral—they drive behavior, whether we intend them to or not.”
“Modern acquisition gives us more tools—like modular contracting, performance-based requirements, and iterative milestones—to build incentives that encourage adaptability, user focus, and collaboration.”
“When you design a contract, ask yourself: If I were the vendor, what behaviors would I focus on to get paid or earn high performance ratings? Do those behaviors match what the mission really needs?”

## Slide 20: Contract Kickoff Sprint 3

## Slide 21: Transition to Post-Award: What Happens Now?
Presented by: [Facilitator Name]
Date: [Session Date]
Notes: Speaker Notes: This section addresses the full ecosystem of post-award readiness. We’ll go beyond logistics and look at how procurement professionals can set the tone for collaboration, define shared understanding, and reduce early delivery risk. Whether you’re the CO, COR, or supporting PO, your leadership in these early phases matters.

## Slide 22: Agenda
Describes strategies to initiate work successfully under a new digital services contract.
Determine the next steps that follow contract award.
Facilitate a tabletop breach exercise as part of ongoing contract oversight and performance monitoring.
Notes: Speaker Notes:

## Slide 23: You’ve Awarded the Contract. Now What?
Kickoff is more than a formality—it’s where delivery success begins.
Even with detailed pre-award discussions, key alignment must still happen.
Contract kickoff ≠ Technical kickoff: both are essential and distinct.
Post-award planning sets the tone for delivery, communication, and accountability.
Notes: Speaker Notes: Now that the contract is awarded, the real work begins. Kickoffs aren’t just boxes to check—they shape how delivery unfolds. In Agile digital services, we can't assume everything carries over cleanly from the solicitation. This section will help you lead or support stronger kickoffs that align both contract structure and Agile execution.

## Slide 24: What’s Your Kick-off Experience?
Think about a recent digital service contract you supported:
What worked well in the kickoff phase?
What caused confusion or slowed things down?
Did the contract and technical teams stay aligned?
How did Sprint 0 (if any) support or stall delivery?
Notes: Speaker Notes:
Before we dive into best practices, let’s ground this in your own experience. Take a minute to think back to a recent contract kickoff—especially one involving software or cloud delivery. What helped? What didn’t? You can jot your thoughts down or share with a partner. This quick reflection will help you connect upcoming content with your real-world context.

## Slide 25: Sprint 0: Establishing Readiness Before Delivery Begins
Purpose of Sprint 0:
Setup phase before formal Agile sprints begin
Critical to digital service contracts—should be included in your roadmap and performance timeline
Aligns people, tools, environments, and expectations
Key Activities:
Onboarding contractor staff (e.g., clearances, GFE, systems access)
Setting up collaboration and tracking tools
Running kickoff meetings and initial delivery planning
Defining DoD, backlog, roadmap, and cadence
Starting discovery or design sprints to inform delivery
Notes: Speaker Notes:
In federal Agile work, Sprint 0 isn’t optional. It’s a necessary bridge between award and execution. You may not be delivering software yet, but critical foundational work is happening.
From clearances and onboarding to backlog planning and kickoff meetings—this phase ensures everyone is equipped to start strong. If you treat Sprint 0 like dead time, you’ll miss the opportunity to shape the team’s delivery conditions.

## Slide 26: Contractual and Technical Kickoffs: Why We Need Both
Two Kickoffs, One Launch Point:
Contract Kickoff: Led by CO & COR
  Align on scope, QASP, success metrics, and administrative procedures.
Technical Kickoff: Led by PO & Vendor Technical Lead
  Align on Agile execution: cadence, tools, team roles, and Definition of Done.
Why Separate Them?
Clarifies responsibilities across business and delivery domains.
Prevents confusion between contractual terms and working methods.
Sets a foundation for communication, escalation, and shared delivery rhythm.
Notes: Speaker Notes:
You’ll typically see two kickoff meetings at the start of a digital services contract—and they serve different purposes. The contract kickoff is your space to get on the same page about what’s in the awarded contract. The technical kickoff is where the delivery team aligns on how the work will actually get done, tracked, and accepted.
This separation helps prevent miscommunication, sets clearer expectations, and gives each role space to lead where they have authority.

## Slide 27: What Makes Cloud Contract Oversight Different?
Federal cloud provisioning requires active government involvement, not vendor-only automation. As a CO or COR, you are responsible for:
Security Compliance: Confirm FedRAMP/FISMA status, incident procedures, and data hosting requirements.
Data Ownership & Governance: Ensure contracts define who owns the data, encryption roles, and offboarding protections.
Access Management: Validate provisioning processes, least privilege controls (RBAC), and audit visibility.
Cost and Resource Monitoring: Require reporting tools and alerts for usage, waste, and budget thresholds.
Notes: Speaker Notes:
Before we jump into our breach activity, let’s ground ourselves in the reality of cloud contract administration. In federal procurement, we can’t just assume the vendor has it all covered. From data control to access permissions and spending alerts—you’re a key player in keeping cloud operations compliant and secure.
Takeaway:
Cloud contracts are dynamic environments—oversight is not passive. COs and CORs must stay in the loop on access, cost, risk, and escalation.

## Slide 28: Activity: Cloud Breach Tabletop Exercise
What is this?
A role-based simulation, not a blame game
Focused on identifying process gaps and improving response clarity
Inspired by disaster recovery tabletop exercises
When to Use:
During contract performance oversight
After onboarding new team members
In preparation for or after policy/contract updates
Notes: Speaker Notes: Today’s activity is a hands-on tabletop exercise designed to help you test how your team would respond to a security breach—using the actual roles and responsibilities you hold in federal Agile delivery.
This is not about finding fault; it’s about surfacing process gaps and improving clarity between COs, CORs, Product Owners, vendors, and security leads. Think of it like a fire drill: we don’t wait for a real fire to find out who’s got the keys to the exit.

## Slide 29: Activity: Cloud Breach Tabletop Exercise
How it Works:
Review the breach scenario.
React as your assigned role: What would you do in the first 6 hours?
Receive updated breach info and revise your role’s response.
Collaborate on a shared incident plan.
Reflect on where coordination succeeded—or failed.
Notes: Speaker Notes: You’ll work in groups, each person taking on a key role—CO, COR, PO, Vendor, or Security SME. You’ll be given a scenario, walk through a simulated breach response, and collaborate on a joint action plan.
Throughout, we’ll pause to reflect on what’s working, what’s unclear, and how contract language, communication protocols, and team coordination play a role in successful breach response. The goal? Leave this room with a better playbook than when you came in.

## Slide 30: Activity: Cloud Breach Tabletop Exercise - Roles
Role | Focus
CO | Contract language enforcement, legal implications, modification authority
COR | Performance tracking, timeline validation, documentation review
PO | Risk to delivery, user impact, coordination with technical teams
Vendor | Detection, reporting, root cause analysis, remediation plan
Security SME | (Optional) Adds realism and guidance on agency-specific requirements
Notes: Speaker Notes: You’ll work in groups, each person taking on a key role—CO, COR, PO, Vendor, or Security SME. You’ll be given a scenario, walk through a simulated breach response, and collaborate on a joint action plan.
Throughout, we’ll pause to reflect on what’s working, what’s unclear, and how contract language, communication protocols, and team coordination play a role in successful breach response. The goal? Leave this room with a better playbook than when you came in.

## Slide 31: Activity: Cloud Breach Tabletop Scenarios
Step 1: Review Your Scenario
Read the scenario carefully as a group.
Identify the potential impact, risks, and affected stakeholders.
Step 2: React by Role
As your assigned role (CO, COR, PO, Vendor, Security SME), respond: “What do I do in the first 6 hours after discovery?”
Use your breach response worksheet to guide your thinking.
Flag uncertainties or gaps in the process.
Step 3: Receive Update #1
Facilitator will share an escalation: breach confirmed with broader scope.
Update your role’s plan accordingly.
Notes: Speaker Notes: You’ll work in groups, each person taking on a key role—CO, COR, PO, Vendor, or Security SME. You’ll be given a scenario, walk through a simulated breach response, and collaborate on a joint action plan.
Throughout, we’ll pause to reflect on what’s working, what’s unclear, and how contract language, communication protocols, and team coordination play a role in successful breach response. The goal? Leave this room with a better playbook than when you came in.

## Slide 32: Cloud Breach Scenarios
Notes: Speaker Notes:
Here’s how we’ll begin. First, your group will receive a scenario—based on real-world patterns we’ve seen in federal digital service delivery. Each of you will respond from your assigned role and walk through what you would do within the first 6 hours of discovering a possible breach.
Don’t worry about getting it ‘right’—this is about testing assumptions, uncovering gaps, and practicing communication across teams. We’ll escalate the scenario with new information partway through, just like in a real event.

## Slide 33: Scenario 1: Delayed Notification
A contractor-managed cloud platform supporting a benefits application detects unauthorized access to log files that include session tokens and metadata. The incident is flagged by the vendor’s monitoring tools at 3:00 AM, and their internal team initiates triage. However, due to unclear escalation procedures and fear of over-reporting, they wait until 10:00 AM to notify the government. The data exposure window remains uncertain.
Notes: Speaker Notes:

## Slide 34: Scenario 2: COR on Leave
A contractor-managed cloud platform supporting a benefits application detects unauthorized access to log files that include session tokens and metadata. The incident is flagged by the vendor’s monitoring tools at 3:00 AM, and their internal team initiates triage. However, due to unclear escalation procedures and fear of over-reporting, they wait until 10:00 AM to notify the government. The data exposure window remains uncertain.

## Slide 35: Scenario 3: Internal Staff Breach
An agency staff member with privileged access to the vendor's cloud dashboard logs in after-hours and initiates several unauthorized queries that result in mass downloads of personally identifiable information (PII). The vendor detects the anomaly but hesitates to report it, unsure whether the activity was authorized. By the time clarification occurs, two days have passed.

## Slide 36: Scenario 4: Partial Data Exposure with Ambiguous Scope
A vendor supporting a shared-service platform discovers that due to a configuration error, access control policies were not applied correctly across tenant environments. An internal audit reveals that external users may have been able to see portions of system configuration logs. It is unclear whether the logs contain any user data or if access was actually exploited.

## Slide 37: Scenario 5: Misrouted Incident Response
A junior developer at the vendor site notices suspicious log traffic and flags it as a potential breach. They follow internal procedures and submit a security incident ticket. However, due to incorrect routing rules, the alert goes to the agency’s Tier 1 help desk instead of security or the COR. The help desk does not escalate it for 48 hours. Once discovered, the scope of the breach has expanded.

## Slide 38: Reflect as a Team
What was your role’s biggest challenge in the scenario?
Where did coordination break down—or work well?
What gaps did you uncover in contract language or escalation paths?
What changes would you make to your team’s current breach readiness?
Notes: Speaker Notes: Let’s come back together and reflect on what we just experienced. Think about your role—what was difficult or unclear? Where did coordination work, and where did it stall?
This debrief is where the value of the exercise really comes through. Capture what surprised you, and let’s talk about how these insights can inform contract language, escalation paths, and internal training.
If this had been a real breach—what would you have wanted in place ahead of time? After-Action Ideas to Share with the Class to Consider:
Clarify or revise breach response clauses
Identify training or documentation needs
Build a follow-up checklist or SOP for future reviews

## Slide 39: Case Study Activity: Laying the Groundwork for Agile Delivery
Notes: Speaker Notes:
Many government teams—and their partners—contribute to advancing digital delivery. These groups create resources, prototypes, and momentum for modern practices.

## Slide 40: Contract Management and Problem Resolution Sprint 4

## Slide 41: Agenda
Describe how to identify and address performance or delivery issues.
Determine how to execute an exit strategy and course correct.
Demonstrate how to negotiate consideration in the context of Agile delivery within federal contracting.

## Slide 42: Executing an Exit Strategy or Course Correction
Even in well-structured Agile contracts, you may need to:
Exit from a vendor relationship
Replace a module or service
Course-correct mid-performance
Common Scenarios:
Modular Integration breakdowns
Persistent performance gaps despite compliance
Interdependencies creating new risks
Conflicting stakeholder perspectives on root cause
Notes: Speaker Notes: Even in Agile environments—especially modular ones—there are moments when you need to decide: do we keep going, adjust course, or exit? These are high-stakes decisions, and they don’t happen in a vacuum. You’ll be weighing contract terms against system dependencies, vendor behavior, and long-term agency goals. Let’s set the stage for how we think through that. Your role as the CO/COR is to:
Analyze contractual, technical, and operational impacts
Balance risk, cost, time, and mission priorities
Document performance, mitigation attempts, and decision rationale

## Slide 43: Balancing Exit vs. Recovery: What Would You Weigh?
Before you terminate or course-correct, consider:
What does the contract say about performance thresholds and remedies?
Is the vendor failing in isolation—or exposing system-wide risks?
What will it take to replace them—technically and administratively?
Are you trading short-term disruption for long-term stability?
Will your choice preserve the modular vision or undermine it?
You don’t need to solve it now—but keep these tradeoffs in mind.
Notes: Speaker Notes: The case study you’ll explore online walks through a situation where these questions weren’t hypothetical—they were urgent. As you work through that material later, use this list as a thinking guide. What you’ll see is that modular flexibility comes with its own form of complexity, especially when interdependencies get tangled.

## Slide 44: Questions?

## Slide 45: Thank you
Contact information
Feedback survey link (if available)